## Sheet1
Phase | Timeline | Goal | Key Activities | Tech Focus
Phase 1: Foundations | Week 1–2 | Learn JavaScript & React Basics | Understand JS syntax, React components, props, state. Build a To-Do app. | React, JS
Phase 1: Foundations | Week 3–4 | Learn React Native | Install Expo, build simple journaling app UI using <View>, <TextInput>, <Button>. | React Native, Expo
Phase 1: Foundations | Week 5–6 | Learn FastAPI & NLP Basics | Create backend endpoints, basic AI sentiment analysis using TextBlob or Hugging Face. | Python, FastAPI, NLP
Phase 2: Prototype | Week 7–9 | Integrate Frontend and Backend | Connect app to FastAPI backend, send entries, receive emotion analysis. | React Native, FastAPI
Phase 2: Prototype | Week 10–12 | Add AI Logic & Alerts | Implement risk detection logic and basic alert notifications. | Python, AI, Notifications
Phase 3: MVP Expansion | Week 13–16 | Create Dashboards | Add privacy dashboards for parents/therapists with emotion trends. | React Native, Charts
Phase 3: MVP Expansion | Week 17–20 | Finalize & Polish MVP | Add authentication, reminders, improve UI, prepare demo video. | Full Stack